## Sheet1
Phase I Project Timeline
Task | Description | Day Start | Day Finish | Task Days Spent
Gather Images | Take images of object to reconstruct from phone | 2021-04-09 | 2021-04-09 | 0
Pairwise Feature matching | OpenCV + SIFT (Medium Article) | 2021-04-09 | 2021-04-12 | 3
Calculate Fundamental Matrix | Given two datasets of 2D points in image coords space, calculate F | 2021-04-12 | 2021-04-14 | 2
Calculate Essential Matrix | Given F and K, get E | 2021-04-14 | 2021-04-16 | 2
Point Triangulation | Also get the relative transform from E via Point Triangulation | 2021-04-16
Formulas:
Day Finish = [Day Start]+[Task Days Spent]
Day Start = [Day Finish, row above]